## Meeting Backlog
| Participant(s) |  |  | Date | Period | Note | Platform
Example | AH | AS | JM | 2021-03-03 | 1 | Consolidate project ideas and choice of algorithms | Blackboard
| AH | AS | JM | 2021-03-09 | 1 | Discussed and visualised choice of algorithms and benchmarking techniques | Blackboard
| AH | AS | JM | 2021-03-16 | 1 | Discussed algorihtmic visualisation tools and reviewed choice of algorithms | Blackboard
| AH | AS | JM | 24/03/21 | 1 | Discussed algorithmic implementation progression and support framework for intended algorithms | Blackboard
| AH | AS | JM | 31/03/21 | 1 | Discussed the contents of the independant literature reviews | Blackboard
| AH | AS | JM | 2021-04-07 | 1 | Discussed algorithmic implementation progression | MS Teams
| AH | AS | JM | 2021-04-14 | 1 | Discussed algorithmic implementation progression | MS Teams
| AH | AS | JM | 2021-04-21 | 1 | Discussed algorithmic implementation progression | MS Teams
| AH | AS | JM | 2021-04-28 | 1 | Discussed algorithmic implementation progression | MS Teams
| AH | AS | JM | 2021-05-05 | 1 | Discussed algorithmic implementation progression | MS Teams
| AH | AS | JM | 2021-05-12 | 1 | Discussed algorithmic implementation progression | MS Teams
| AH | AS | JM | 2021-05-15 | 8 | Finalising algorithmic implementations of the Pac-Man application | MS Teams
| AH | AS | JM | 2021-05-16 | 8 | Finalising algorithmic implementations of the Pac-Man application | MS Teams
| AH | AS | JM | 2021-05-17 | 8 | Finalising algorithmic implementations of the Pac-Man application | MS Teams
| AH | AS | JM | 2021-05-18 | 8 | Finalising algorithmic implementations of the Pac-Man application | MS Teams
| AH | AS | JM | 2021-05-19 | 8 | Finalising algorithmic implementations of the Pac-Man application | MS Teams
| AH | AS | JM | 2021-05-20 | 8 | Finalising algorithmic implementations of the Pac-Man application | MS Teams
| AH | AS | JM | 2021-05-21 | 8 | Progressing with the collaborative passages of the conference paper | MS Teams
| AH | AS | JM | 2021-05-22 | 12 | Progressing with the collaborative passages of the conference paper | MS Teams
| AH | AS | JM | 2021-05-23 | 15 | Progressing with the collaborative passages of the conference paper | MS Teams
| AH | AS | JM | 2021-05-24 | 4 | Progressing with the projects presentation preparation | MS Teams
| AH | AS | JM | 25/05/21 | 4 | Project submission overview
|  |  |  | Total | 102

## Activity Log
| Participant | Time | Date | Activity
Example | AS | 1 | 2021-03-10 | Pac-Man game repository setup
| JM | 8 | 2021-03-10 | Setting up original Pac-Man for group use
| AH | 8 | 2021-03-10 | Setting up original Pac-Man for group use
| AS | 8 | 2021-03-10 | Setting up original Pac-Man for group use
| AH | 2 | 2021-03-11 | Group management file setup
| AH | 1 | 2021-03-12 | Group management file setup
| AH | 1 | 2021-03-16 | Visualisation tool scouting
| AH | 1 | 2021-04-07 | Group management file maintenance
| AH | 1 | 2021-04-19 | Group management file maintenance
| AH | 8 | 2021-05-14 | Scoring method implementation
| AH | 2 | 2021-05-14 | Debug mode method implementation
| JM | 8 | 14/05/2021 | Setting up Pac-Man | Name | Initials | Time
| AS | 8 | 13/05/2021 | Setting up Pac-Man | Jack Moorin | JM | 101
| AH | 5 | 2021-05-15 | A* library solution implementaton | Arpit Sharma | AS | 120
| AH | 2 | 2021-05-15 | A* solution implementation | Adam Hubble | AH | 145
| AH | 4 | 2021-05-15 | Conference paper format and styling
| JM | 8 | 15/05/2021 | Iterative testing benchmark setup |  | Total | 366
| JM | 4 | 15/05/2021 | Designed Pac-Man and ghost icons
| JM | 8 | 16/05/2021 | Joint implementation of Dijkstra with AS
| AS | 8 | 16/05/2021 | Joint implementation of Dijkstra with JM
| AH | 8 | 2021-05-16 | A* solution implementation
| AH | 8 | 2021-05-16 | A* solution implementation
| AS | 3 | 2021-05-17 | Shortest from all algorithm implementation
| JM | 8 | 17/05/2021 | Implementation of IDDFS algorithm
| AH | 4 | 2021-05-17 | A* solution implementation
| AH | 2 | 2021-05-17 | Refactor A* library solution implementation
| AH | 8 | 2021-05-17 | Refactor A* solution implementation
| AS | 8 | 17/05/2021 | Bidirectional BFS solution implementation
| AS | 8 | 18/05/2021 | Bidirectional BFS solution implementation
| AH | 8 | 18/05/2021 | Implemented A* heuristic catalogue
| AS | 9 | 18/05/2021 | Bidirectional Dijkstra solution implementation
| AH | 8 | 19/05/2021 | Bidirectional A* solution implementation
| AH | 2 | 19/05/2021 | Iterative testing benchmark refactor
| AS | 8 | 19/05/2021 | Bidirectional A* solution implementation with AH
| JM | 1 | 19/05/2021 | Bidirectional A* solution implementation with AH
| JM | 8 | 19/05/2021 | Conference paper common contribution
| AH | 12 | 20/05/2021 | Conference paper common contribution
| AS | 10 | 20/05/2021 | Conference paper common contribution
| JM | 8 | 20/05/2021 | Conference paper common contribution
| AH | 12 | 21/05/2021 | Conference paper common contribution
| AS | 12 | 21/05/2021 | Conference paper common contribution
| JM | 12 | 21/05/2021 | Conference paper common contribution
| AS | 5 | 22/05/2021 | Travelling Salesperson Problem (TSP) attempt
| AH | 15 | 22/05/2021 | Conference paper common contribution
| AS | 10 | 22/05/2021 | Conference paper common contribution
| JM | 12 | 22/05/2021 | Conference paper common contribution
| AH | 15 | 23/05/2021 | Conference paper common contribution
| AS | 15 | 23/05/2021 | Conference paper common contribution
| JM | 8 | 23/05/2021 | Conference paper common contribution
| AH | 8 | 24/05/2021 | Presentation creation and finalisation
| JM | 8 | 24/05/2021 | Presentation creation and finalisation
| AS | 8 | 24/05/2021 | Presentation creation and finalisation